## Sheet1
| Week | Frontend | Backend | CI | CD | Effort Level
2023-03-06 | 1 | Project Setup | Build Code | GitHub Repo |  |  | Low
2023-03-13 | 2 | Build Trello |  | Create Makefile + Scripts |  |  | Medium
2023-03-20 | 3 | Build Project Plan Sheet |  | Testing |  |  | Medium - time intensive
2023-03-27 | 4 |  |  | Configure GitHub Actions |  |  | Very Involved
2023-04-03 | 5 |  |  | Test GitHub Actions
2023-04-10 | 6 | Test |  |  | Azure Pipeline Configuration
2023-04-17 | 7 |  |  |  | Locust setup
2023-04-24 | 8 | QA |  |  | Create WebApps
2023-04-24 | 8 |  |  |  | Deploy Resources in ADO
2023-05-01 | 9 | Submission